## CPM
Critical Path Method
HELP | [15 empty] | © 2010-2022 Vertex42 LLC
| Start Date | [7 empty] | Days to Completion | [7 empty] | Get the Pro version
| 2022-05-16 | [7 empty] | #N/A |  |  |  | Critical tasks |  |  |  | • more predecessors (up to 10)
| 2022-08-06 | [11 empty] | No successor defined yet |  |  |  | • more tasks (up to 500)
| #N/A | [6 empty] | Times (in Days)
[9 empty] | Time Distribution: | Triangular | [5 empty] | [42] | [19 empty] | Series Used in the Gantt Chart
ID | Task Name | Predecessors (Enter one ID per cell) | [5 empty] | O (min) | M (most likely) | P (max) | Duration (exp. time) | ES | EF | LS | LF | Slack |  | EF of Predecessors | [5 empty] | Successors | [5 empty] | LS of Successors | [5 empty] | ES | Critical | +T | -T | Duration | +T | -T | Slack | Milestone
0 | Start | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | -0.25 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
1 | Online Search | [6 empty] | 3 | 6 | 9 | 6 | 0 | 6 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 6 | 3 | 3 | #N/A | #N/A | #N/A | 0 | #N/A
2 | Literature Review | [6 empty] | 4 | 7 | 10 | 7 | 0 | 7 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 12 | [5 empty] | 0 |  | 0 | 7 | 3 | 3 | #N/A | #N/A | #N/A | 0 | #N/A
3 | Project Brief | [6 empty] | 3 | 4 | 7 | 4.6667 | 0 | 4.6667 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 12 | [5 empty] | 0 |  | 0 | 4.6667 | 2.3333 | 1.6667 | #N/A | #N/A | #N/A | 0 | #N/A
4 | Project Specs | [6 empty] | 3 | 4 | 7 | 4.6667 | 0 | 4.6667 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 12 | [5 empty] | 0 |  | 0 | 4.6667 | 2.3333 | 1.6667 | #N/A | #N/A | #N/A | 0 | #N/A
5 | Paper Demo | [6 empty] | 3 | 4 | 7 | 4.6667 | 0 | 4.6667 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | 10 |  |  |  |  | 0 | 0 |  |  |  | 0 | 4.6667 | 2.3333 | 1.6667 | #N/A | #N/A | #N/A | 0 | #N/A
6 | Charts & Networks | [6 empty] | 1 | 3 | 5 | 3 | 0 | 3 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 10 |  |  | 13 |  |  | 0 |  |  | 0 | 0 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A
7 | Implementation | [6 empty] | 4 | 8 | 11 | 7.6667 | 0 | 7.6667 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [5 empty] | 0 |  |  |  |  | 0 | 7.6667 | 3.3333 | 3.6667 | #N/A | #N/A | #N/A | 0 | #N/A
8 | Career Consulting | [6 empty] | 5 | 7 | 8 | 6.6667 | 0 | 6.6667 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 13 | [5 empty] | 0 | 0 | 6.6667 | 1.3333 | 1.6667 | #N/A | #N/A | #N/A | 0 | #N/A
9 | Midterm PPT and Presentation | 7 | 5 |  |  |  |  | 7 | 10 | 11 | 9.3333 | 7.6667 | 17 | 0 | 0 | 0 |  | 7.6667 | 4.6667 | 0 | 0 | 0 | 0 |  |  |  | 11 |  | 13 |  |  |  | 0 |  | 0 | 7.6667 | 9.3333 | 1.6667 | 2.3333 | #N/A | #N/A | #N/A | 0 | #N/A
10 | Testing | 5 | 6 |  |  |  |  | 11 | 17 | 19 | 15.6667 | 4.6667 | 20.3333 | 0 | 0 | 0 |  | 4.6667 | 3 | 0 | 0 | 0 | 0 |  |  |  | 11 |  | 13 |  |  |  | 0 |  | 0 | 4.6667 | 15.6667 | 3.3333 | 4.6667 | #N/A | #N/A | #N/A | 0 | #N/A
11 | Revise, Redo | 10 | 9 |  |  |  |  | 11 | 17 | 19 | 15.6667 | 20.3333 | 36 | 0 | 0 | 0 |  | 20.3333 | 17 | 0 | 0 | 0 | 0 | [5 empty] | 13 | [5 empty] | 0 | 20.3333 | 15.6667 | 3.3333 | 4.6667 | #N/A | #N/A | #N/A | 0 | #N/A
12 | Results, Conclusions, Future Work | 2 | 3 | 4 |  |  |  | 7 | 12 | 13 | 10.6667 | 7 | 17.6667 | 0 | 0 | 0 |  | 7 | 4.6667 | 4.6667 | 0 | 0 | 0 | [5 empty] | 13 | [5 empty] | 0 | 7 | 10.6667 | 2.3333 | 3.6667 | #N/A | #N/A | #N/A | 0 | #N/A
13 | Written Report + PPT + Presentation | 12 | 11 | 10 | 9 | 8 | 6 | 5 | 13 | 14 | 10.6667 | 36 | 46.6667 | 0 | 0 | 0 |  | 17.6667 | 36 | 20.3333 | 17 | 6.6667 | 3 | [12 empty] | 36 | 10.6667 | 3.3333 | 5.6667 | #N/A | #N/A | #N/A | 0 | #N/A
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
1000 | Finish | 100 | 200 | [7 empty] | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A | #N/A | 0 | 0 | 0 | 0 | [12 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Note on B5: Finish Date: The Finish Date uses the WORKDAY() function to calculate the date to completion, excluding weekends and the holidays listed in the Holidays worksheet. If you see a #NAME or other error in the Finish Date, you probably need to install the Analysis ToolPak and then recalculate the worksheet by pressing Ctrl+Alt+F9.
Note on A8: Task ID: Normally, you would start by assigning IDs as 10, 20, 30, etc. However, the ID can be anything you want, including text.
Note on B8: Task Name: The task name is a description that will show up in the gantt chart. The task name will be bolded if the task is a critical task. This is done through conditional formatting.
Note on C8: Predecessors: The set of events immediately preceding the task. In a network diagram or PERT chart, the predecessors for a particular task are all the tasks which have arrows pointing to that particular task. - Each predecessor needs to refer to the ID in column A. Successors: The set of events immediately following a particular task. In a network diagram or PERT chart, arrows are drawn from a task to its successors.
Note on I8: Optimistic Time (O): The minimum time required to complete the task. Assumes that everything proceeds faster than normal.
Note on J8: Most Likely Time (M): The most likely time required to complete the task, assuming everything proceeds as normal.
Note on K8: Pessimistic Time (P): The maximum time required to complete the task. Assumes that everything proceeds slower than normal.
Note on L8: Duration or Expected Time: Using a Beta distribution, where O is the minimum, P is the maximum, and M is the most likely value, the formula for calculating the mean or expected time is: Duration = (O+4M+P)/6 Using a Triangular distribution, the mean of the distribution would be: Duration = (O+M+P)/3
Note on M8: Early Start Time: The ES is the maximum EF of all predecessors, except for the first task where the ES=0.
Note on N8: Early Finish Time: The EF time is the ES time plus the duration (EF=ES+Duration).
Note on O8: Late Start Time: The LS time is calculated as the LF time minus the duration (LS=LF-Duration).
Note on P8: Late Finish Time: The LF time is the minimum LS of all the successors, except for the last task where LF equals EF.
Note on Q8: Slack Time: The Slack time is calculated as LF minus EF. It can also be calculated as LS minus ES. If the slack is zero, then the task is on the critical path.

## Holidays
Holidays to Exclude from Working Days
See help (F1) on the WORKDAY() function
This worksheet lets you create a list of dates to be excluded from the number of Working Days. The WORKDAY() function already excludes weekends, so you only need to list dates for holidays and other non-working days. If your project spans more than one year, make sure you add dates for each year. The named range, holidays, is a dynamic named range ending at the last blank cell in column A. The comments column is just for your reference.
Date | Non-Working Days
2019-01-01 | New Year's Day
2020-01-01
2019-12-25 | Christmas
2010-12-25

## ©
Critical Path Method
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/critical-path-method.html
© 2010-2022 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.